## Read Me
FDE FIELD LAB — 45-DAY INTENSIVE
A practical learning and delivery tracker for one Support Operations Copilot capstone.
REALISTIC OUTCOME
In 45 days, build one well-understood capstone demonstrating discovery, deterministic full-stack delivery, evaluated AI, controlled LangGraph orchestration, hybrid retrieval, safe enterprise integration, production operation, and impact communication. This is a strong foundation and portfolio project—not a promise of complete field readiness.
HOW TO USE THIS WORKBOOK
Work 3–4 focused hours on six days, then use each seventh day as a gate/review day. Filter the 45-Day Plan by phase or status. Record your notes and evidence. If a gate fails, close the evidence gap before advancing merely because the calendar changed.
DEFAULT LAB STACK — CONFIRMED OR CHANGED ON DAY 6
Frontend: React + TypeScript. API/contracts: Python, FastAPI, Pydantic. Transactional data: PostgreSQL, SQLAlchemy, Alembic. Testing: pytest and Playwright. Agent orchestration: LangGraph only from Day 20. Retrieval: vector plus BM25/keyword comparison. Integration: typed tools, webhook, one read-only MCP capability. Delivery/operations: Docker, GitHub Actions, OpenTelemetry-compatible telemetry. These are lab choices, not the definition of an FDE.
DAILY METHOD
Learn one concept and failure mode → explain it → design it against the Northstar workflow → build the smallest useful behavior → break a plausible wrong implementation → record evidence and the next decision.
PROGRESSION RULE
The dependency path is: customer outcome → deterministic product → evaluated model → durable graph → authorized retrieval → safe integration → production evidence → pilot and case study. Frameworks are introduced only when a scenario requirement justifies them.
Progress summary
Complete | In Progress | Blocked | Not Started

## 45-Day Plan
45-DAY DAILY PLAN
Filterable roadmap: purpose, technicality, build, integration, evidence, and company relevance for every day.
Day | Phase | Daily objective | Why this day | Technicality introduced | Hands-on build | How it connects / integrates | Verification & evidence | MNC relevance | Startup relevance | Effort | Status | Learner notes / evidence links
1 | Discovery & design | Understand the customer problem before building | Technology is premature until the user and desired improvement are clear. | FDE delivery loop; customer problem; output vs outcome; metric; guardrail; assumption. No framework introduced. | Define fictional Northstar Cloud, map its support workflow, analyze ticket E-1042, and draft a guarded customer outcome. | Creates the outcome against which every later API, model, retrieval, and tool decision will be judged. | Standalone HTML lesson; scenario artifact; user/workflow/outcome/guardrail checklist. | Creates shared language across product, support, security, legal, and engineering. | Prevents limited runway from funding an impressive solution to the wrong problem. | 3–4 h | Complete — revised
2 | Discovery & design | Separate facts, hypotheses, and questions | Unverified beliefs must not silently become requirements. | Evidence classification; assumption register; stakeholder mapping; open vs leading interview questions. | Create a fact/assumption register and interview guides for support, security, and engineering stakeholders. | Tests Day 1’s problem statement and supplies evidence needed for workflow and architecture decisions. | Every claim labelled with source, confidence, owner, validation method, and due date. | Improves alignment where knowledge is distributed across many teams. | Finds the riskiest unknown quickly without heavy research overhead. | 3–4 h | Not Started
3 | Discovery & design | Map the current workflow, delays, errors, and risks | The largest visible inconvenience may not be the real bottleneck. | Swimlane mapping; handoffs; queue time vs active time; failure modes; risk/impact scoring. | Produce an as-is workflow from ticket arrival to approved response, with delay and risk annotations. | Turns Day 2 evidence into the current-state model used for scope and metrics. | Workflow reviewed for actors, systems, handoffs, waits, rework, errors, and sensitive actions. | Exposes cross-team queues and governance dependencies. | Identifies the smallest bottleneck that can create immediate value. | 3–4 h | Not Started
4 | Discovery & design | Define user stories, acceptance criteria, and non-goals | Clear behavior boundaries prevent scope creep and ambiguous demos. | User stories; Given/When/Then acceptance criteria; functional vs non-functional requirements; explicit non-goals. | Specify intake, triage, search, draft, review, escalation, and approval behavior. | Converts the workflow into testable product contracts without selecting implementation details. | Each priority story has positive, negative, and authorization acceptance criteria. | Supports traceability and formal stakeholder sign-off. | Keeps the first release narrow enough to ship and learn. | 3–4 h | Not Started
5 | Discovery & design | Design baseline metrics and target hypotheses | Improvement cannot be claimed without a before state and measurement definition. | Median vs mean; percentile; sampling; leading/lagging metrics; quality and safety guardrails. | Define measurement events for response time, routing correctness, evidence quality, and unauthorized actions. | Operationalizes Day 1’s outcome and informs later telemetry and evaluation datasets. | Metric dictionary with numerator, denominator, timestamp boundaries, segments, data source, and caveats. | Makes ROI and governance review auditable across business units. | Enables fast go/no-go decisions based on evidence. | 3–4 h | Not Started
6 | Discovery & design | Design system context and trust boundaries | Architecture should follow actors, data sensitivity, constraints, and failure impact. | C4 context/container views; data flow; trust boundaries; synchronous vs asynchronous work; ADR format. Default stack proposed: React/TypeScript, FastAPI/Pydantic, PostgreSQL. | Draw context and container diagrams; write ADR-001 selecting the smallest viable baseline stack. | Uses Days 2–5 constraints to confirm or change the default lab stack before implementation. | Architecture review covers ownership, PII, identity, external dependencies, failure paths, and rejected alternatives. | Fits enterprise architecture, security review, and ownership boundaries. | Avoids premature microservices while documenting when the design must evolve. | 3–4 h | Not Started
7 | Discovery & design | Run the customer gate review and correct the plan | A review day prevents calendar progress from replacing evidence-based progress. | Design review; requirement traceability; decision log; gap closure; retrospective. | Present outcome, workflow, requirements, metrics, and architecture; revise contradictions and unresolved risks. | Locks the minimum product contract that Phase 2 will implement. | Gate checklist passed or a documented remediation plan replaces advancement. | Models steering committee and architecture review communication. | Creates a founder/customer checkpoint before engineering spend increases. | 2–3 h | Not Started
8 | Deterministic product | Model domain objects and legal state transitions | A stable domain model prevents UI, API, database, and agents from inventing different meanings. | Python type hints; Pydantic models; enums; finite-state machine; invariants. | Define Ticket, Recommendation, Evidence, Approval, Decision, and Run; implement allowed transitions. | Becomes the shared language for API schemas, database records, tools, and LangGraph state. | Unit tests reject illegal transitions and preserve valid ones. | Clarifies contracts and team ownership in larger codebases. | Reduces rework by putting business rules in one place. | 3–4 h | Not Started
9 | Deterministic product | Define API and idempotency contracts | Distributed clients need explicit success, error, retry, and duplicate-request behavior. | HTTP semantics; REST; JSON; FastAPI/OpenAPI; Pydantic validation; RFC 7807-style errors; idempotency keys. | Design ticket, recommendation, review, and history endpoints before implementing storage. | Exposes Day 8 domain rules through a versioned boundary usable by UI and integrations. | Contract tests cover valid requests, malformed input, conflict, not-found, authorization placeholder, and duplicate submission. | Supports independent frontend/backend teams and integration governance. | Allows parallel work while avoiding accidental API drift. | 3–4 h | Not Started
10 | Deterministic product | Design the relational schema and indexes | Durable constraints belong in the database, not only application code. | PostgreSQL; PK/FK; UNIQUE/CHECK/NOT NULL; normalization; transactions; B-tree/composite indexes; ER diagram. | Model tenants, users, tickets, recommendations, decisions, approvals, and append-only audit events. | Persists Day 8 states and Day 9 API resources with integrity and query paths. | Schema review plus EXPLAIN-ready query/index rationale and constraint-failure tests. | Meets integrity, audit, reporting, and scale expectations. | Provides one dependable datastore before adding infrastructure. | 3–4 h | Not Started
11 | Deterministic product | Implement migrations and repository data access | Repeatable schema evolution and isolated persistence are prerequisites for safe delivery. | SQLAlchemy 2; Alembic migrations; transaction boundaries; repository pattern only where it removes coupling; pytest fixtures. | Create initial migration and persistence methods for tickets, recommendations, decisions, and history. | Connects domain rules to PostgreSQL while keeping HTTP and future graph nodes independent of SQL details. | Upgrade/downgrade in a clean database; rollback-on-failure; uniqueness and concurrency-focused data tests. | Supports controlled releases and multiple environments. | Avoids manual database fixes and accelerates iteration. | 3–4 h | Not Started
12 | Deterministic product | Build ticket intake and rule-based triage | A simple deterministic baseline reveals whether AI adds real value later. | FastAPI endpoint implementation; rule engine; normalization; deterministic confidence/reason codes. | Accept a ticket, validate it, persist it, and create a rule-based category/priority recommendation. | Implements the first end-to-end behavior using Days 8–11 contracts. | Unit and API tests include E-1042, ambiguous text, malformed input, and duplicate requests. | Provides explainable fallback behavior and auditability. | Ships useful triage early without model cost or dependency risk. | 3–4 h | Not Started
13 | Deterministic product | Build human review and immutable decision history | Human accountability must be represented as data, not implied by a prompt. | Optimistic concurrency/versioning; append-only audit events; accept/edit/reject workflow; actor and timestamp provenance. | Add APIs to review recommendations and record every decision without overwriting history. | Creates the approval boundary later model and tool actions must obey. | Tests stale edits, repeated decisions, actor attribution, and complete history reconstruction. | Supports compliance, investigations, and controlled operations. | Makes feedback immediately available for product learning. | 3–4 h | Not Started
14 | Deterministic product | Build the operator UI and browser workflow | The product must support a real human task, not only expose APIs. | React + TypeScript; accessible forms; async UI states; typed API client; validation and error recovery. | Create ticket intake, queue, recommendation review, evidence placeholder, and history views. | Connects the browser to Phase 2 APIs and preserves the human decision boundary. | Keyboard/accessibility checks and Playwright browser test from intake through review. | Demonstrates usability and adoption considerations to operations teams. | Creates a customer-testable vertical slice quickly. | 4 h | Not Started
15 | Deterministic product | Verify the full baseline and run a product gate | AI experimentation needs a trusted comparison system. | Test pyramid; pytest unit/integration/API tests; Playwright E2E; boundary-value testing; retrospective. | Run browser-to-database demo; test failures; document baseline latency and rule accuracy. | Freezes the deterministic baseline that Days 16–22 must beat or safely fall back to. | Clean setup; migration; API/UI tests; traceable demo; defects and decisions recorded. | Provides release evidence and cross-team demo confidence. | Prevents AI work from hiding basic product defects. | 3–4 h | Not Started
16 | Evaluated model & graph | Create a labelled evaluation dataset and scoring baseline | Model quality cannot be assessed from a few attractive examples. | JSONL/CSV eval cases; independent labels; train/dev/test separation concept; precision, recall, F1, confusion matrix. | Label representative ticket categories, priorities, risky actions, and expected escalation behavior; score deterministic rules. | Creates the fixed comparison set for prompts, models, routing, and graph changes. | Dataset schema checks; label rationale; class distribution; deterministic baseline report. | Supports model governance and reproducible approval evidence. | Avoids selecting models from demos or intuition. | 3–4 h | Not Started
17 | Evaluated model & graph | Add a model adapter with validated structured outputs | Model responses are untrusted external data and must satisfy an application contract. | Provider-neutral model interface; Pydantic structured output; JSON schema; timeout; parse/validation failure; test fake. | Implement ticket classification behind an adapter; reject or repair invalid schema without silently accepting it. | Replaces only one Day 12 rule capability while preserving API and fallback behavior. | Tests valid, malformed, missing-field, extra-field, timeout, and provider-error responses. | Allows provider governance and substitution without rewriting product logic. | Keeps experimentation reversible and testable. | 3–4 h | Not Started
18 | Evaluated model & graph | Version prompts and compare small versus large models | Model choice should match task difficulty, quality, latency, and cost. | Prompt/config versioning; token counting; temperature control; model routing experiment; eval reproducibility. | Evaluate a smaller/faster model and a larger reasoning model on the Day 16 dataset. | Adds evidence for the routing policy while retaining the same Day 17 output contract. | Report quality, p50/p95 latency, input/output tokens, estimated cost, and failure examples by model/version. | Supports approved-model catalogs and spend governance. | Uses expensive models only where the quality difference matters. | 3–4 h | Not Started
19 | Evaluated model & graph | Implement routing budgets and deterministic fallback | Model APIs are unreliable dependencies; the customer workflow must still function. | Policy router; task/risk classification; latency and token budgets; fallback chain; cache boundaries; abstention. | Route simple classification to the small model, risky/ambiguous work to stronger handling, and failures to rules or human review. | Uses Day 18 evidence to choose routes and preserves Day 12 deterministic behavior. | Route matrix tests prove model choice, budget enforcement, fallback, and abstention for asymmetric cases. | Controls vendor risk, cost allocation, and regulated use cases. | Protects margin and responsiveness during provider failures. | 3–4 h | Not Started
20 | Evaluated model & graph | Separate workflow state from durable history and introduce LangGraph | Graph orchestration is justified only now that branching, retry, and approval needs are concrete. | LangGraph StateGraph; TypedDict/Pydantic state; pure nodes; edges; reducers; ephemeral run state vs PostgreSQL business history. | Model intake → validate → classify → route → prepare-review as minimal nodes and edges. | Orchestrates existing deterministic/model functions; it does not replace domain rules, persistence, or authorization. | Node contract tests plus diagram showing what belongs in graph state, database history, and retrieved context. | Makes long-running workflow control explicit and reviewable. | Adds only the orchestration needed for known branches. | 4 h | Not Started
21 | Evaluated model & graph | Add conditional routing, checkpoint, interrupt, and resume | Human approval and process restarts require durable execution position. | Conditional edges; stable run ID; LangGraph checkpointer; interrupt/resume; idempotent node design; correlation IDs. | Pause before human review, persist checkpoint, simulate restart, then resume exactly once after a decision. | Connects Day 13’s durable decision boundary to Day 20’s graph execution. | Restart test proves state recovery, no duplicate side effects, correct route, and audit/run correlation. | Supports durable processes and operational recovery. | Prevents a restart from losing work or repeating costly calls. | 4 h | Not Started
22 | Evaluated model & graph | Evaluate complete outputs and traces; simplify where possible | A correct final answer can hide unsafe or wasteful intermediate behavior. | Trajectory/trace evaluation; node assertions; regression thresholds; checkpoint inspection; architecture simplification review. | Evaluate final classification plus route, model selection, fallback, approval pause, and number of calls. | Turns Day 16 cases into graph-level regression tests and checks whether LangGraph earns its complexity. | AI gate report; restart evidence; trace failures; decision to keep, simplify, or remove each graph element. | Supports governance of model behavior and process evidence. | Stops orchestration complexity from growing without measurable benefit. | 3–4 h | Not Started
23 | Hybrid retrieval | Build source manifest, parsing, and normalization | Retrieval quality begins with traceable, clean source data—not embeddings. | Source manifest; MIME/type checks; parser interface; Unicode normalization; document checksum; malformed-input quarantine. | Ingest approved support documents into normalized text plus source metadata and parsing status. | Creates authorized, versioned inputs for both keyword and vector indexing. | Parser fixtures cover valid, malformed, duplicate, oversized, and unsupported documents. | Provides lineage, ingestion governance, and reproducibility. | Avoids poisoning indexes with bad or duplicate content. | 3–4 h | Not Started
24 | Hybrid retrieval | Create semantic chunks with stable identity and versions | Chunking controls retrieval granularity, update behavior, and citation accuracy. | Structure-aware chunking; overlap trade-offs; stable chunk IDs; content hashes; metadata; document/chunk versions. | Chunk headings and paragraphs while preserving tenant, source, section, version, and checksum. | Transforms Day 23 normalized documents into units shared by vector and keyword indexes. | Tests stable IDs, changed/unchanged chunks, metadata inheritance, and boundary cases. | Enables incremental indexing, lineage, retention, and audit. | Reduces re-embedding cost when only part of a document changes. | 3–4 h | Not Started
25 | Hybrid retrieval | Build vector retrieval and a recall baseline | Semantic search helps when wording differs, but it must be measured. | Embeddings; vector dimensions; cosine similarity; pgvector/HNSW concepts; top-k; Recall@k. | Embed chunks, create a vector index, retrieve against labelled support questions, and record misses. | Indexes Day 24 chunks and returns candidate evidence to the future response step. | Recall@k report includes paraphrases, domain terms, empty results, and wrong-tenant prevention placeholder. | Supports large knowledge corpora and semantic discovery. | Improves usefulness without model training. | 4 h | Not Started
26 | Hybrid retrieval | Build keyword/BM25 retrieval for exact identifiers | Vector similarity can miss error codes, product IDs, names, and rare exact terms. | Tokenization; normalization; inverted index; term/document frequency; BM25; phrase/exact identifier handling. | Index the same chunks with a BM25-capable keyword baseline and test E-1042-like identifiers. | Creates a second retriever over identical stable chunk IDs so results can be compared and fused. | Tests exact codes, acronyms, phrase queries, common words, typo behavior, and large-document updates. | Handles enterprise identifiers, policy numbers, and technical vocabulary. | Provides cheap, explainable search and complements embeddings. | 4 h | Not Started
27 | Hybrid retrieval | Fuse ranks, manage context, cite evidence, and abstain | More retrieved text can increase cost and distract the model rather than improve answers. | Reciprocal Rank Fusion; optional reranking; deduplication; context/token budget; citation mapping; confidence and abstention. | Combine vector and keyword candidates, select bounded evidence, produce citations, and abstain when support is weak. | Feeds only authorized, relevant Day 24 chunks into the model contract and preserves source lineage. | Tests cases where vector wins, keyword wins, both conflict, evidence is absent, and context exceeds budget. | Supports defensible answers and controlled model spend. | Improves quality while limiting latency and tokens. | 4 h | Not Started
28 | Hybrid retrieval | Enforce tenant/ACL filters and incremental freshness | Correct retrieval is unsafe if it leaks another customer’s data or serves deleted content. | Pre-filtered retrieval; tenant/ACL metadata; upsert; tombstone/delete; re-index queue; freshness lag; reconciliation. | Apply access filters before ranking; update one document; remove one; prove index/database convergence. | Adds authorization and lifecycle behavior to both Day 25 and Day 26 indexes. | Cross-tenant denial, revoked-access, update, deletion, stale-index, and reconciliation tests. | Meets isolation, retention, and controlled knowledge-update requirements. | Allows frequent content updates without full reindexing. | 4 h | Not Started
29 | Hybrid retrieval | Compare vector, keyword, and hybrid retrieval | The retrieval design should be selected from query evidence, not fashion. | Recall@k; Precision@k; MRR/nDCG concepts; latency; index cost; error slicing. | Run the same labelled queries through all three strategies and document which query types each serves best. | Chooses the production retrieval path and parameters used by later tools and response generation. | Retrieval gate report plus citation, ACL, freshness, and deletion evidence. | Supports architecture and vendor decisions with measurable trade-offs. | Avoids operating expensive infrastructure that adds no value. | 3–4 h | Not Started
30 | Enterprise integration | Implement authentication, RBAC, tenancy, and audit schema | Tools and retrieved data require identity and authorization before integration. | OIDC/JWT validation concepts; sessions; RBAC; tenant scoping; least privilege; audit actor/resource/action/result. | Add identities and roles for support agent, lead, security reviewer, and service; enforce tenant scope. | Protects all existing API, retrieval, approval, and future tool boundaries. | Authentication, role matrix, object ownership, cross-tenant, expired-token, and audit tests. | Aligns with SSO, segregation of duties, and compliance controls. | Provides secure customer separation without enterprise-scale complexity. | 4 h | Not Started
31 | Enterprise integration | Threat-model prompts, content, PII, and secrets | Retrieved documents and tickets are untrusted content, not instructions. | STRIDE-style threat modeling; prompt injection; content/instruction separation; PII minimization/redaction; secret handling; exfiltration paths. | Create data-flow threat model and implement the highest-priority input/output protections. | Applies threats to model, retrieval, logs, tools, MCP, and approval boundaries before writes exist. | Adversarial tickets/documents cannot override policy, reveal secrets, cross tenants, or leak PII into logs. | Supports security review, privacy, and customer assurance. | Prevents a pilot-ending trust incident. | 3–4 h | Not Started
32 | Enterprise integration | Create typed read and write tools with policy enforcement | Agent tools are APIs; prose prompts cannot enforce contracts or permissions. | Pydantic tool schemas; machine-readable results; read/write separation; allowlists; authorization at execution; idempotency. | Implement read_ticket/search_evidence and a guarded propose_ticket_update tool; keep direct mutation outside the model. | Exposes existing application capabilities to the graph without bypassing Day 30 controls. | Schema, malformed argument, unauthorized actor, wrong tenant, duplicate request, and machine-readable error tests. | Creates governed integration contracts and audit points. | Makes automation safe enough to incrementally expand. | 4 h | Not Started
33 | Enterprise integration | Process webhooks safely and reconcile state | External systems retry, reorder, duplicate, and occasionally lose events. | HMAC signature verification; timestamp/nonce; replay window; idempotent consumer; ordering; reconciliation job; rate-limit handling. | Build a ticket-created webhook adapter and periodic reconciliation against a realistic external-system stub. | Feeds external tickets into Day 12 intake while preserving stable IDs, audit, and exactly-once effects over at-least-once delivery. | Invalid signature, replay, duplicate, out-of-order, transient failure, and missed-event recovery tests. | Matches enterprise SaaS integration reliability expectations. | Prevents duplicate customer work with a small robust adapter. | 4 h | Not Started
34 | Enterprise integration | Implement immutable, expiring approval proposals | Approval must cover the exact action executed, not a changed request. | Canonical payload; proposal hash; immutable snapshot; TTL/expiry; reject/edit/re-propose; compare-and-execute; separation of duties. | Let the copilot propose a write, show exact effects, obtain authorized approval, then execute once if unchanged and unexpired. | Connects Day 13 human decisions, Day 21 graph interrupt, and Day 32 write tool safely. | Stale, edited, expired, duplicated, self-approved, unauthorized, and post-approval mutation tests. | Supports high-impact workflow governance and forensic evidence. | Enables useful automation without granting autonomous write access. | 4 h | Not Started
35 | Enterprise integration | Add one allowlisted read-only MCP capability | MCP is useful for standardized capability discovery, not as a reason to expose every internal action. | MCP host/client/server model; tool/resource contracts; capability allowlist; schema negotiation; timeout; trust boundary. | Expose one read-only support knowledge or ticket lookup capability through an MCP server and consume it from the host. | Wraps an already-authorized Day 32 read function; MCP does not own business logic or permissions. | Discovery, valid call, denied capability, malformed response, timeout, unavailable server, and audit correlation tests. | Supports standardized integration with controlled capability exposure. | Demonstrates interoperability without risky write access. | 4 h | Not Started
36 | Enterprise integration | Run hostile integration and isolation tests | Security claims require negative evidence at the real system boundaries. | Adversarial testing; confused deputy; TOCTOU; cross-tenant access; hostile MCP/tool output; stale approval; audit completeness. | Execute an attack matrix across API, retrieval, tools, webhook, approval, and MCP paths; fix high-risk failures. | Validates the complete Phase 5 trust model rather than isolated happy paths. | Threat-model findings closed or explicitly accepted with owner and mitigation date. | Produces evidence for security and architecture gates. | Finds trust failures before customer rollout. | 3–4 h | Not Started
37 | Production & challenge | Instrument sanitized end-to-end traces and cost | Without correlated telemetry, agent failures look like random bad answers. | OpenTelemetry concepts; structured logs; trace/span IDs; model/retrieval/tool/approval spans; token/cost metrics; PII redaction. | Trace one ticket from HTTP request through graph, retrieval, model, tool proposal, approval, and result. | Correlates all components built so far using run, tenant, ticket, and request identifiers without logging sensitive content. | Trace completeness test; redaction test; latency/token/cost fields present by step. | Supports centralized observability, audit, and model governance. | Makes debugging and cost optimization practical for a small team. | 4 h | Not Started
38 | Production & challenge | Add timeouts, bounded retries, fallback, and circuit behavior | Retries without classification can multiply cost, latency, and duplicate effects. | Timeout budget; transient vs permanent errors; exponential backoff with jitter; retry cap; circuit breaker; fallback; retry-safe operations. | Apply policies separately to model, embedding, MCP, webhook target, and database dependencies. | Uses Day 37 traces to observe decisions and preserves Day 19/32 deterministic fallbacks and idempotency. | Injected timeout, 429, 5xx, invalid response, open/half-open circuit, budget exhaustion, and fallback tests. | Meets dependency resilience and vendor-risk requirements. | Protects user experience and cloud spend during outages. | 4 h | Not Started
39 | Production & challenge | Design queue, recovery, and side-effect reconciliation | Long-running work must survive restarts and at-least-once execution. | Job queue; lease/visibility timeout; at-least-once delivery; idempotent consumer; dead-letter handling; backpressure; reconciliation. | Move ingestion or long model work to a worker; crash it between proposal and completion; recover without duplicate effects. | Extends Day 21 checkpointing and Day 33 reconciliation to asynchronous execution. | Crash/restart, duplicate delivery, poison message, queue saturation, and side-effect uncertainty tests. | Supports scalable workers and recoverable operations. | Decouples slow work without introducing unbounded complexity. | 4 h | Not Started
40 | Production & challenge | Create reproducible delivery, CI gates, and rollback | A working laptop demo is not a deployable service. | Docker/Compose; GitHub Actions; lint/type/test/security gates; migration job; staged environments; health/readiness; rollback. | Containerize services, run CI on a clean checkout, deploy to staging, migrate, smoke-test, and rehearse rollback. | Packages the complete system and blocks releases that fail earlier contracts or evaluations. | Pipeline artifact; staged URL; migration log; smoke result; rollback evidence. | Fits controlled change management and environment promotion. | Creates repeatable delivery without a large platform team. | 4 h | Not Started
41 | Production & challenge | Define SLOs, dashboards, alerts, load test, and game day | Operating readiness requires measurable reliability and actionable failure response. | SLI/SLO/error budget; Prometheus-compatible metrics concepts; dashboard; alert thresholds; load model; runbook; game day. | Set availability/latency/quality targets, load representative traffic, inject one dependency failure, and follow the runbook. | Uses Day 37 telemetry and Days 38–40 recovery controls under realistic demand. | Dashboard, actionable alert, load report, recovery timeline, runbook update, and game-day findings. | Supports on-call, capacity planning, and service ownership. | Reveals limits before a customer pilot and keeps alerts focused. | 4 h | Not Started
42 | Production & challenge | Implement one bounded multi-agent comparison variant | Multiple agents are justified only if role separation beats a simpler workflow. | Specialist/reviewer roles; typed handoff schema; bounded turns; independent context; stop conditions; shared-state risks. | Add a specialist draft plus reviewer critique/revise variant for one difficult ticket class, with strict call limits. | Runs beside—not instead of—the single controlled graph so both can use the same data, tools, and evaluation cases. | Handoff schema, max-turn, contradictory advice, failure propagation, and no-infinite-loop tests. | Evaluates specialized workflows without committing the whole platform. | Tests potential quality gains before accepting extra latency and cost. | 4 h | Not Started
43 | Production & challenge | Compare single versus multi-agent and keep the winner | Architecture complexity must earn its operational cost with measurable improvement. | Paired experiment; quality rubric; latency/cost/failure rate; statistical uncertainty concept; error slicing; decision ADR. | Run identical hard cases through both variants and retain, narrow, or delete the multi-agent path. | Uses Day 16 labels, Day 22 trace evaluation, and Day 37 cost telemetry for an architecture decision. | Comparison report and ADR include quality, p95 latency, tokens, cost, failure modes, and chosen scope. | Provides defensible architecture governance. | Avoids maintaining an expensive pattern that does not improve outcomes. | 3–4 h | Not Started
44 | Forward deployment | Run a customer-style demo and pilot simulation | Delivery success depends on adoption, observed workflow behavior, and feedback—not test results alone. | Demo narrative; rollout cohort; enablement; feature flag; feedback coding; adoption funnel; support log. | Run representative users through ticket intake, evidence, recommendation, approval, failure, and recovery; prioritize one iteration. | Exercises the complete product against Day 1 outcome and Day 5 measurement plan. | Demo checklist, structured feedback, adoption/usage events, support issues, and one prioritized change. | Models controlled rollout, training, and stakeholder communication. | Creates fast customer learning before wider investment. | 4 h | Not Started
45 | Forward deployment | Produce impact report, architecture defense, and case study | An FDE must explain customer value, technical judgment, limitations, and next steps. | Before/after analysis; guarded claim; architecture trade-off narrative; cost/value summary; case-study structure; competency evidence. | Implement the chosen pilot iteration; present outcome metrics, failures, architecture decisions, demo, and roadmap. | Closes the loop from Day 1 outcome through production evidence and updates the competency rubric. | Reproducible case study, linked evidence, honest limitations, before/after metric, and next decision. | Communicates to executives, customer teams, security, and engineering panels. | Communicates product value to founders, customers, and hiring teams. | 4 h | Not Started

## Phase Overview
PHASE OVERVIEW
Seven evidence gates keep the 45-day intensive ordered by delivery dependency rather than hype.
Days | Phase | Why in this order | Build outcome | Gate evidence | Your gate decision / notes
1–7 | Discovery & solution definition | Understand the user, workflow, constraints, and success measure before selecting technology. | Discovery pack, requirements, architecture context, first ADR. | Facts vs assumptions; workflow map; acceptance criteria; baseline plan; architecture review.
8–15 | Deterministic full-stack baseline | Create a reliable product and human workflow before adding probabilistic AI. | Ticket intake, rule triage, review UI, relational history. | Browser-to-database demo; migration; unit, API, and browser tests.
16–22 | Evaluated model & controlled graph | Require model value over a baseline before accepting orchestration complexity. | Structured model classification, routing, fallback, LangGraph checkpoint and approval pause. | Labelled evaluation; routing tests; checkpoint/restart/resume test.
23–29 | Grounded hybrid retrieval | Establish retrieval quality, freshness, citations, and authorization before generation. | Incremental ingestion, vector and keyword indexes, hybrid retrieval, citations. | Recall/MRR comparison; ACL, deletion, freshness, citation, and abstention tests.
30–36 | Enterprise tools, security & MCP | Add integrations only after identity, authorization, and approval boundaries exist. | RBAC, typed tools, replay-safe webhook, approval flow, one read-only MCP capability. | Threat model; hostile input; cross-tenant; unauthorized-write; stale-approval; MCP failure tests.
37–43 | Production & architecture challenge | Prove that the system survives dependency failures and that added complexity is justified. | Traces, reliability controls, CI/CD, staged deployment, game day, multi-agent comparison. | Dashboard; pipeline; load/failure exercise; single-versus-multi evaluation report.
44–45 | Forward deployment evidence | Finish with adoption, outcome measurement, feedback, and communication. | Customer-style demo, pilot simulation, iteration decision, case study. | Feedback record; before/after result; architecture defense; updated rubric.

## Technical Index
TECHNICAL INDEX
When each major capability appears, where it becomes deeper, why it exists, and when not to use it.
Capability / framework | First introduced | Deepened / evaluated | Purpose in this lab | Do not use it as…
Customer discovery | 1–7 | 44–45 | User workflow, evidence, metrics, constraints, feedback, and impact. | Do not replace interviews and measurement with model-generated assumptions.
React + TypeScript | 14 | 44 | Accessible operator UI and typed browser/API boundary. | Do not build UI before core workflow and API contracts are clear.
Python + Pydantic | 8 | 17, 20, 32 | Typed domain, API, model, graph-state, and tool contracts. | Pydantic validates structure; it does not enforce authorization by itself.
FastAPI + OpenAPI | 9 | 12–14, 30–34 | Versioned HTTP boundary with validation and machine-readable errors. | Do not expose graph internals directly as the public API.
PostgreSQL | 10 | 11, 13, 20–21, 28, 30 | Durable business state, constraints, history, tenancy, and checkpoints. | Do not treat a vector store as the source of transactional truth.
SQLAlchemy + Alembic | 11 | 40 | Transactional data access and reproducible schema evolution. | Avoid repository abstractions that only wrap one call without reducing coupling.
pytest + Playwright | 8 | 15 onward | Domain, API, integration, browser, failure, and regression evidence. | Do not count “did not crash” as correctness.
Model adapter / structured output | 17 | 18–22 | Provider-neutral model calls with schema validation and fallback. | Do not trust free-form model text as an application contract.
Model routing | 18 | 19, 37–38 | Use the smallest sufficient model based on task, risk, quality, cost, and latency. | Do not route only by prompt length or use the largest model everywhere.
LangGraph | 20 | 21–22, 34, 39 | Explicit branching, checkpoint, interrupt/resume, and controlled recovery. | Do not use it for a simple linear function chain or to replace domain logic.
Evaluation datasets | 16 | 18–19, 22, 25–29, 43 | Compare behavior against independent labels and regression thresholds. | Do not select architecture from a few hand-picked demos.
Vector retrieval / pgvector | 25 | 27–29 | Semantic retrieval when query and source use different wording. | Do not depend on it alone for exact identifiers or access control.
Keyword / BM25 retrieval | 26 | 27–29 | Exact identifiers, rare terms, phrases, and explainable lexical relevance. | Do not assume keyword search handles paraphrases well.
Hybrid retrieval / RRF | 27 | 28–29 | Combine complementary vector and lexical rankings with bounded context. | Do not add fusion if evaluation shows one retriever is sufficient.
OIDC/JWT, RBAC, tenancy | 30 | 31–36 | Identity, role policy, object ownership, and customer isolation. | Never delegate authorization decisions to prompts or model judgment.
Typed tools | 32 | 33–36 | Strict read/write contracts, validation, authorization, idempotency, and structured errors. | Do not expose broad shell, SQL, or write capabilities to the model.
Webhooks | 33 | 36, 38–39 | Verified external events with replay protection and reconciliation. | Do not assume external delivery is unique, ordered, or guaranteed.
Approval gate | 13 | 21, 34, 36 | Human accountability over an immutable, exact, expiring proposed action. | A model saying “approved” is not authorization.
MCP | 35 | 36–38 | Standard discovery and invocation of one allowlisted read-only capability. | Do not expose every internal function or autonomous writes merely because MCP supports tools.
OpenTelemetry / observability | 37 | 38–45 | Correlated traces, metrics, sanitized logs, token use, cost, and audit. | Do not log raw prompts, secrets, or PII by default.
Resilience patterns | 38 | 39–41 | Timeouts, bounded retries, backoff, circuit behavior, queues, recovery, and reconciliation. | Do not retry permanent failures or uncertain writes blindly.
Docker + GitHub Actions | 40 | 41, 44–45 | Reproducible build, quality gates, staged release, migration, and rollback. | Do not confuse containerization with operational readiness.
Multi-agent variant | 42 | 43 | Bounded specialist/reviewer experiment with typed handoffs and stop conditions. | Do not keep it unless measured quality gains justify extra cost, latency, and failure modes.

## _Lists (hidden)
Not Started
In Progress
Complete
Complete — revised
Blocked